## Slide 1: ETpathfinder workshop
2024-01-31
Towards the commissioning of the Beamsplitter Tower
WP4/WP5 Planning
Kenny Lam for ETpathfinder team
ET-xxxxxxx

## Slide 2: Overview
Where are we now?
How to build a Beam Splitter Tower
  Details on order
  Some tuning details
Planning

## Slide 3: Where are we now?
DN300 Gate Valve troubleshooting
Start of Vacuum Line installation
Completion of LN2 Infrastructure
Water-Water chillers installed
LN2 supply tank installed
Drilling feedthroughs
Vacuum Manifold installed
HRTS Assembly
1st of 6 Bench GAS filters tuned
6 Towers interconnected!
LN2 Tub production started

## Slide 4: Where are we now?
Almost all parts are delivered and cleaned!
  Pre-Isolation Stage parts being cleaned
  More orders ongoing, such as water cooling pipes, cables, etc.
First few stepper motor assemblies put together
Anchor holes for various components
Successful evacuation with roughing lines

## Slide 5: How to build your own Beam Splitter tower
Step 1
Dummy IP feet and baseplate for installation
Dismantle vacuum tower up to bottom vessel
Hoist the whole internal mechanics assembly into the open vessel
Build internal mechanics on dummy IP feet
Close tower
BS Path
Step 2
Step 3
Step 4
Step 5

## Slide 6: How to build your own Beam Splitter tower
Dummy IP feet and baseplate for installation
Dismantle vacuum tower up to bottom vessel
Hoist the whole internal mechanics assembly into the open vessel
Build internal mechanics on dummy IP feet

## Slide 7: Step 3: Building up the internal mechanics
Dummy Baseplate
and IP feet
2. Bottom IP Ring
3. Bench Locking
Mechanism
4. Bench and
population
5. IP legs and
supports
6. LVDT
Base Ring
7. Safety platforms
and GAS filters
8. Top IP ring and
accessories
9. Top GAS filter
10. Routing in-vacuum
cabling

## Slide 8: Step 3.5: Tuning the internal mechanics
Starting state:
All systems are locked to their respective safety frames.
All GAS Filters have been individually tuned beforehand
Equalizing the load between the 4 IP Legs (Done during installation)
Tune Bench CoM and bring to correct working height
Suspend (i.e. unlock) Bench from GAS F2 and tune wire length according to bench working height
Suspend GAS F2 from GAS F1 and tune wire length according to bench working height
Suspend GAS F1 from GAS F0 and tune wire length according to bench working height
F2
F1
F0
Bench height for
tuning reference

## Slide 9: Are the stars aligned?
In addition to the roadmap topics:
Dummy Baseplate and IP Feet
Custom hoisting tool
Optical components
Assembly tooling
Scaffolding sufficient?
Power distribution
(Partial) DAQ?
Control schemes?
Etc.
Etc..
Input appreciated!

## Slide 10: The road ahead
For 2024:
Focus on the commissioning of the first Bench Tower by June/July. Fingers crossed for 2 Bench Towers?
Finish all infrastructure-related topics.

## Slide 11: The road ahead
For 2025 and onward:
Mirror tower commissioning focus
Chances to pull some cryogenics work to 2024 with the help from IFAE?

## Slide 12: Questions

## Slide 13: Open items
LVDTs and Actuators. Timeline?
In-vacuum cables
Populating optical table in or outside tower? When?
HRTS suspensions. When?
Vacuum system
  Lifting system
  Vacuum controls
  Venting system
  Baking and isolation
  Gate valves cleanliness dispute
Auxiliary systems
  Cable trays
  Power distribution
  Cooling system
  Compressed air
  Signal cabling: in-air cables, E-racks, patch panels, stress relief
Logistics
  Shipping container outside DUB30?
  Room for storage inside ETpf cleanroom?
Who
UAntwerp?
UM?
UCLouvain?
UAntwerp?
KIT
Nikhef
Nikhef
Nikhef

## Slide 14: Planning 2023
LVDTs and actuators in
Fasteners in
Vacuum infrastructure
LN2 SAT
More open items …
Water cooling
Clean parts in
In-vacuum cabling in