## ATLAS
[22 empty] | LS4 1/2 |  | LS4 2/2
|  |  |  | Optional |  | Q2/2026-Q1/2027 |  | Q2/2027-Q1/2028 |  | Q2/2028-Q1/2029 |  | Q2/2029-Q1/2030 |  | Q2/2030-Q1/2031 |  | Q2/2031-Q1/2032 |  | Q2/2032-Q1/2033 |  | Q2/2033-Q1/2034 |  | Q2/2034-Q1/2035 |  | Q2/2035-Q1/2036
Description of Activity | Nikhef Project | Deliverable Type | FASTTRACK WP | Cost (MEUR) |  | Type | FTE | Type | FTE | Type | FTE | Type | FTE | Type | FTE | Type | FTE | Type | FTE | Type | FTE | Type | FTE | Type | FTE
Sensors | ATLAS upgrade | MoU | WP1.3 LGAD Hybrids | 0.4 | 1.24 | [8 empty] | ME | 0.1 | ME | 0.05
[14 empty] | EA | 0.1 | EA | 0.05 | [8 empty] | NB: production level work (wafer probe etc)
ASICs | ATLAS upgrade | MoU | WP2.1 Hybrid ASICs | 0.15 | [11 empty] | EA | 0.1 | EA | 0.1 | EA | 0.1 |  |  |  |  | NB: Local solution to connect DAQ with ASIC or module characterisation (ASIC part here)
High Speed Link | Common LHC DAQ NetFELIX | MoU | WP3.1 High-Speed Transmission | 0.05 | [20 empty] | 0.2
DAQ (hw, fw, sw) | Common LHC DAQ NetFELIX | MoU | WP3.2 DAQ | 0.15 |  |  |  | EA | 0.05 | EA | 0.1 | EA | 0.05 | EA | 0.05 | EA | 0.05 | [8 empty] | NB: carrier board etc
[6 empty] | EB | 0.1 |  |  |  |  | EB | 0.1 | EB | 0.1 | [6 empty] | EB | 0.05 | EB | 0.05 | NB: modify fw accordingly
[6 empty] | CA | 0.1 | CA | 0.05 | CA | 0.1 | CA | 0.05 | CA | 0.1 | CA | 0.1 | CA | 0.05 |  |  |  |  | CA | 0.1 | NB: readout sw (low level communication)
Electronics, Cable and Power Supply | ATLAS upgrade | MoU | WP4.3 Mechanics & Infrastructure | 0.08 | [11 empty] | EE | 0.4 | EE | 0.4 | [5 empty] | 0.1
Module Production | ATLAS upgrade | MoU | WP4.1 Module Construction | 0.25 | [11 empty] | MF | 0.8 | MF | 0.4 | MF | 0.1
[16 empty] | MD | 0.2 | MD | 0.2 | MD | 0.1
Integration & Commissioning | ATLAS upgrade | MoU | WP4.3 Mechanics & Infrastructure | 0.08 |  | MD | 0.25 | MD | 0.25 | [10 empty] | EE | 0.5 | EE | 0.6 |  | 0.8 | [TBC] to verify if MT needed or not? If so, what category (I assume some level but we can also rely on sending EE people to CERN and use cern mechanics resource)
Computing* | AI tracking | MoU | WP5.1 Accelerators, WP5.2 Algorithms | 0.08 |  |  |  | CC | 0.05 | CC | 0.1 | CC | 0.2 | CC | 0.4 | CC | 0.2 | CC | 0.2 | CC | 0.1 |  |  |  |  | [TBC] Which category under CT? higher FTE needed? If so, when? Any common strategy with AI & PDP?
Sensor Submission | ATLAS upgrade | R&D | WP1.3 LGAD Hybrids | 0.15 | 1.06 | [20 empty] | NB: material only, no engineer needed
Sensor R&D (lab, testbeam) | ATLAS upgrade | R&D | WP1.3 LGAD Hybrids | 0.18 |  |  |  | ME | 0.1 | ME | 0.4 | ME | 0.1
[8 empty] | EA | 0.1 | EA | 0.6 | EA | 0.7 | EA | 0.1 | EA | 0.1 | [8 empty] | NB: incl. carrier board, ASIC hybridisation for R&D
Radiation* | ATLAS upgrade | R&D | WP1.3 LGAD Hybrids | 0.05 |  | ME | 0.3 | ME | 0.1
[6 empty] | EA | 0.2 | EA | 0.1 | [16 empty] | NB: radiation infrastructure from scratch
Module, QA R&D | ATLAS upgrade | R&D | WP4.1 Module Construction | 0.4 | [7 empty] | ME | 0.6 | ME | 0.8
[12 empty] | EE | 0.4 | EE | 0.2 | [10 empty] | [TBC] we need system engineer, which one is it in MT?
Serializer & Data Aggregation* | Common LHC DAQ NetFELIX | R&D | WP3.1 High-Speed Transmission | 0.06 |  |  |  | EA | 0.025 | EA | 0.025 | EA | 0.025 | EA | 0.1 | EA | 0.1 | EA | 0.1 | EA | 0.1 |  |  |  |  | [Q] EA does also packaging and interface?
[10 empty] | ED | 0.025 | ED | 0.025 | ED | 0.05
Optical Power R&D* | ATLAS upgrade | R&D | WP4.3 Mechanics & Infrastructure | 0.06 |  | EA | 0.05 | EA | 0.05 | EA | 0.05 | EA | 0.05 | EA | 0.05 | EA | 0.05 | EA | 0.05 | EA | 0.05 | EA | 0.05 | EA | 0.05 | NB: R&D efforts, without further 4D detector or cross experiments application
Trigger with timing | ATLAS upgrade, AI tracking | R&D | WP5.1 Accelerators, WP5.2 Algorithms | 0.08 |  | CA | 0.05 | CA | 0.05 | CA | 0.05 | CA | 0.05 | CA | 0.05 | CA | 0.05 | CA | 0.05 | CA | 0.2 | CA | 0.2 | CA | 0.2
Unforseen R&D Infrastructure | ATLAS upgrade | R&D | WP1.3 LGAD Hybrids, WP2.1 Hybrid ASICs, WP 4.3 Mechanics & Infrastructure | 0.08 |  |  | 0.05 |  | 0.05 |  | 0.05 |  | 0.1 |  | 0.1 |  | 0.1 |  | 0.05 |  | 0 |  | 0 |  | 0
Unforseen material (10% of MoU) |  | Contingency | All WP's | 0.124 | 0.248
Unforseen T.P. (10% of MoU) |  | Contingency | All WP's | 0.124
|  |  |  | 2.3 |  | 1.1 |  | 0.975 |  | 1.5 |  | 2.45 |  | 2.3 |  | 2.35 |  | 1.6 |  | 1.25 |  | 0.9 |  | 1.5
|  |  |  | in proposal: |  | 1.64 |  | 2.47 |  | 2.38 |  | 1.99 |  | 1.87 |  | 1.75 |  | 1.77 |  | 1.08 |  | 0.79 |  | 0.76
Note: | 1) electronics modification relies on international collaborators |  |  |  |  | Prepare infrastructure |  | Sensor R&D |  | Sensor R&D |  | Sensor final |  | Sensor production |  | Wafer production, die, etc |  |  |  | Production, QA |  | Integration Surface |  | Installation, Commissioning
| 2) mechanics/vessel relies on international collaborators |  |  |  |  | DAQ & Integration for current HGTD | [5 empty] | prepare Module |  | Module R&D |  | Module Final, QA R&D |  | Full-scale Demonstrator
3) AI tracking and Common LHC DAQ NetFELIX are placeholders for the potential Nikhef global projects
Legend | * Computing: data processing & trigger (may incl. ML, AI), object reconstruction incl. tracking and forward objects reco in 4D
* Radition: cold probe station, cold box at laser setup, cold box at test beam, stoarge and handling of post-radiated sensor/modules
* Serializer & Data Aggregation: work following our DRD7 committement from FE (Integrated photonics) to BE (ethernet, server) - both Nikhef & Nijmegen
* Optical Power R&D: work following our DRD7 committement on WADAPT (Wu)

## LHCb
Optional
Description of Activity | Nikhef Project | Deliverable Type | FASTTRACK WP | Cost (MEUR) |  | Q2/2026-Q1/2027 | Q2/2027-Q1/2028 | Q2/2028-Q1/2029 | Q2/2029-Q1/2030 | Q2/2030-Q1/2031 | Q2/2031-Q1/2032 | Q2/2032-Q1/2033 | Q2/2033-Q1/2034 | Q2/2034-Q1/2035 | Q2/2035-Q1/2036
Sensors | VELO Modules | MoU | WP1.1 3D Hybrids | 0.94 | 4.468 | 0.33MC¦0.33MD | 0.33MC¦0.33MD | 0.33MC | 0.33MC | 0.33MC | 0.33MC | 0.33MC | 0.33MC | 0.33MC | 0.33MC
ASICs | VELO ASIC | MoU | WP2.1 Hybrid ASICs | 1.73
ASIC serializers | VELO ASIC | MoU | WP3.1 High-Speed Transmission
DAQ | Common LHC DAQ | MoU | WP3.2 Data Acquisition | 0.2
Power Supply Contribution | VELO Design/Mechanics/Infrastructure | MoU | WP3.2 Data Acquisition | 0.04
RF Shield | VELO Design/Mechanics/Infrastructure | MoU | WP4.3 Mechanics & Infrastructure | 0.13
Module Production | VELO Modules | MoU | WP4.1 Module Construction | 0.628
Layout & Construction | VELO Design/Mechanics/Infrastructure | MoU | WP4.3 Mechanics & Infrastructure | 0.8
Common Funds |  | MoU-CF | WP5.1 Accelerators | 1.4893 | 1.4893
Sensor Submission | Sensor R&D | R&D/Engineering | WP1.1 3D Hybrids | 0.2 | 2.98
ASIC Submission | Picopix R&D | R&D/Engineering | WP2.1 Hybrid ASICs | 0.6
Assembly manufacture | Sensor R&D | R&D/Engineering | WP1.1 3D Hybrids | 0.05
Wafer thinning/metallization | Sensor R&D | R&D/Engineering | WP1.1 3D Hybrids | 0.06
Irradiation | Picopix R&D,Sensor R&D | R&D/Engineering | WP1.1 3D Hybrids,WP2.1 Hybrid ASICs | 0.06
Characterisation | Sensor R&D | R&D/Engineering | WP1.1 3D Hybrids | 0.15
Cooling R&D | VELO Design/Mechanics/Infrastructure | R&D/Engineering | WP4.2 Cooling | 0.05
Cooling substrate R&D | VELO Module | R&D/Engineering | WP4.1 Module Construction | 0.1
Module Production Infrastructure | VELO Module | R&D/Engineering | WP4.1 Module Construction | 0.61
50% of Wafer Testing Equipment | Picopix R&D | R&D/Engineering | WP2.1 Hybrid ASICs | 0.05
Electrical characterization of die | Picopix R&D | R&D/Engineering | WP2.1 Hybrid ASICs | 0.1
1/3 of Automatic probe station | Picopix R&D | R&D/Engineering | WP2.1 Hybrid ASICs | 0.15
High-speed serializer R&D | Picopix R&D | R&D/Engineering | WP3.1 High-Speed Transmission | 0.5
Cooling Plant R&D | VELO Design/Mechanics/Infrastructure | R&D/Engineering | WP4.2 Cooling | 0.1
Unforseen R&D Infrastructure | Picopix R&D,Sensor R&D | R&D/Engineering | WP1.1 3D Hybrids,WP2.1 Hybrid ASICs | 0.2
Unforseen material (10% of MoU) |  | Contingency | All WP's | 0.4468 | 0.8936
Unforseen T.P. (10% of MoU) |  | Contingency | All WP's | 0.4468
8.9373

## ALICE
Optional
Description of Activity | Nikhef Project | Deliverable Type | FASTTRACK WP | Cost (MEUR) |  | Q2/2026-Q1/2027 | Q2/2027-Q1/2028 | Q2/2028-Q1/2029 | Q2/2029-Q1/2030 | Q2/2030-Q1/2031 | Q2/2031-Q1/2032 | Q2/2032-Q1/2033 | Q2/2033-Q1/2034 | Q2/2034-Q1/2035 | Q2/2035-Q1/2036
Sensors | ALICE Project 1 | MoU | WP1.2 Monolithic | 0.3 | 5.3
DAQ | ALICE Project 1 | MoU | WP3.1 High-Speed Transmission | 0.2
Module Design | ALICE Project 1 | MoU | WP4.1 Module Construction | 0.3
Module Cooling | ALICE Project 2 | MoU | WP4.2 Cooling | 0.3
Layout & Construction | ALICE Project 2 | MoU | WP4.3 Mechanics & Infrastructure | 1.2
Module Assembly | ALICE Project 1 | MoU | WP4.1 Module Construction | 0.2
Cooling | ALICE Project 2 | MoU | WP4.2 Cooling | 0.3
ASIC Design | Alice Project 3 | MoU | WP2.2 Monolithic | 0
High Speed links | Alice Project 3 | MoU | WP3.1 High-Speed Transmission | 0.3
DAQ | Alice Project 3 | MoU | WP3.2 Data Acquisition | 0.7
Common Funds (Sensors) |  | MoU-CF | WP1.2 Monolithic | 0.5
Common Funds (DAQ) |  | MoU-CF | WP3.2 Data Acquisition | 0.5
Common Funds (Infrastructure) |  | MoU-CF | WP4.3 Mechanics & Infrastructure | 0.25
Common Funds (Computing) |  | MoU-CF | WP5.2 Algorithms | 0.25
Sensor Submission | ALICE Project 1 | R&D | WP1.2 Monolithic | 1
Sensor Characterization | ALICE Project 1 | R&D | WP1.2 Monolithic | 0.4
Digital Characterization | Alice Project 3 | R&D | WP2.2 Monolithic | 0.4
Sensor R&D | Alice Project 1 | R&D | WP1.2 Monolithic,WP2.2 Monolithic | 0 | 2.8
DAQ R&D | Alice Project 3 | R&D | WP3.2 Data Acquisition | 0.1
Module R&D | ALICE Project 1 | R&D | WP4.1 Module Construction | 0.2
Mechanics R&D | ALICE Project 2 | R&D | WP4.3 Mechanics & Infrastructure | 0.2
Computing R&D | Alice Project 1 | R&D | WP5.1 Accelerators ,WP5.2 Algorithms | 0.5
Unforseen material (10% of MoU) |  | Contingency | All WP's | 0.53 | 1.06
Unforseen T.P. (10% of MoU) |  | Contingency | All WP's | 0.53
8.1

## Proposal-Internal
|  |  | WP1 Sensors | [5 empty] | WP2 ASICs |  |  |  | WP3 Readout |  |  |  | WP4 Mechanics & Cooling | [5 empty] | WP5 IT Infrastructure, Data & Software |  |  |  | Partial Totals Material | Partial Totals Personnel | Total Material | Total Personnel
|  |  | WP1.1 3D Hybrids Material | WP1.1 3D Hybrids Personnel | WP1.3 LGAD Hybrids Material | WP1.3 LGAD Hybrids Personnel | WP1.2 Monolithic Material | WP1.2 Monolithic Personnel | WP2.2 Monolithic Material | WP2.2 Monolithic Personnel | WP2.1 Hybrid ASICs Material | WP2.1 Hybrid ASICs Personnel | WP3.1 High-Speed Transmission Material | WP3.1 High-Speed Transmission Personnel | WP3.2 Data Acquisition Material | WP3.2 Data Acquisition Personnel | WP4.1 Module Construction Material | WP4.1 Module Construction Personnel | WP4.2 Cooling Material | WP4.2 Cooling Personnel | WP4.3 Mechanics & Infrastructure Material | WP4.3 Mechanics & Infrastructure Personnel | WP5.1 Accelerators Material | WP5.1 Accelerators Personnel | WP5.2 Algorithms Material | WP5.2 Algorithms Personnel
ALICE | Detector | Sensor |  |  |  |  | 0.3 | 0.0935 | [18 empty] | 3.8 | 7.2157 | 8.1 | 7.9293
|  | Mechanics | [10 empty] | 0.2 | 0.81992 |  |  | 0.3 |  | 0.3 |  | 1.2 | 2.8729
|  | Module Assembly | [14 empty] | 0 | 0.77373 |  |  | 0.2
|  | Cooling | [16 empty] | 0.3 | 0.89984
|  | Readout | [7 empty] | 0.0935 |  |  | 0.3 | 0.81992 | 0.7 | 0.84242
|  | Power | [18 empty] | 0
| Common Funds | Common Funds |  |  |  |  | 0.5 | [7 empty] | 0.5 | [5 empty] | 0.25 |  |  |  | 0.25 |  | 1.5 | 0
| R&D | Sensor Submission Costs |  |  |  |  | 1 | [19 empty] | 2.3 | 0.187
|  | Characterisation |  |  |  |  | 0.4 |  | 0.4
|  | R&D | [5 empty] | 0.0935 |  | 0.0935 |  |  |  |  | 0.1 |  | 0.2 |  |  |  | 0.2
| Computing | Computing | [20 empty] | 0.25 |  | 0.25 | 0.52658 | 0.5 | 0.52658
ATLAS | Detector | Detector |  |  | 0.5 | [21 empty] | 0.5 | 0 | 2.3 | 1.65
| Common Funds | Common Funds | [24 empty] | 0 | 0
| R&D | Characterisation |  |  | 0.3 | 0.15 | [20 empty] | 1.8 | 1.15
|  | Sensor/ASIC | 0.5 | [7 empty] | 0.5 | 0.5
|  | Readout | [12 empty] | 0.2 | 0.25
|  | Cooling | [16 empty] | 0.3 | 0.25
| Computing | Computing | [23 empty] | 0.5 | 0 | 0.5
LHCb | Detector | Sensors | 0.94 | 0.645 | [22 empty] | 4.468 | 12.5038 | 8.9373 | 13.0038
|  | ASICs | [8 empty] | 1.73 | 1.9996
|  | (reduced) DAQ | [11 empty] | 1.1633 | 0.2 | 1.1633
|  | Power Supply Contribution | [12 empty] | 0.04
|  | (reduced) RF Shield | [18 empty] | 0.13 | 0.65563
|  | Module Production | [14 empty] | 0.628 | 2.7273
|  | Layout & Construction | [18 empty] | 0.8 | 4.1496
| Common Funds | (reduced, to be checked) Common Funds | [20 empty] | 1.4893 |  |  |  | 1.4893 | 0
| R&D | Sensor Submission | 0.2 | [23 empty] | 2.78 | 0.5
|  | ASIC Submission | [8 empty] | 0.6
|  | Assembly manufacture | 0.05
|  | Wafer thinning/metallization | 0.06
|  | Irradiation Costs | 0.03 | [7 empty] | 0.03
|  | Characterisation | 0.15
|  | Cooling R&D | [16 empty] | 0.05 | 0.3
|  | Cooling substrate R&D | [14 empty] | 0.1
|  | Module Production Infrastructure | [14 empty] | 0.61
|  | (reduced to 50%) Wafer Testing Equipment | [8 empty] | 0.05
|  | Electrical characterization of die | [8 empty] | 0.1
|  | (contribute 1/3) Automatic probe station | [8 empty] | 0.15
|  | High-speed serializer R&D | [10 empty] | 0.5
|  | Cooling Plant R&D | [16 empty] | 0.1 | 0.2
| Unforseen | Unforseen R&D Infrastructure | 0.1 | [7 empty] | 0.1 | [15 empty] | 0.2 | 0
(reduced to zero) Unforseen Personnel
| Computing | Computing | [24 empty] | 0 | 0
PDP | Preproduction Materia for technical readiness | Purchase costs | [20 empty] | 0.35 |  |  |  | 1.4 | 0 | 1.4 | 0.6
|  | System costs | [20 empty] | 0.35
|  | Power costs | [20 empty] | 0.35
|  | Cooling costs | [20 empty] | 0.35
| Personnel | Personnel | [21 empty] | 0.6 |  |  | 0 | 0.6
R&D | Blue Sky | Prototyping | 0.1 |  | 0.1 |  | 0.1 |  | 0.1 |  | 0.1 | [15 empty] | 0.5 | 0 | 1 | 0
| Characterisation | Common Infrastructure | 0.1 |  | 0.1 |  | 0.1 |  | 0.1 |  | 0.1 | [15 empty] | 0.5 | 0
|  | Total Detector + Common Funds | 0.94 | 0.645 | 0.5 | 0 | 0.8 | 0.0935 | 0 | 0.0935 | 1.73 | 1.9996 | 0.5 | 2.8032 | 1.44 | 2.0057 | 0.928 | 3.5011 | 0.6 | 0.89984 | 2.58 | 7.6781 | 1.4893 | 0 | 0.25 | 0
|  | Total R&D and computing | 1.29 | 0 | 0.5 | 0.15 | 1.6 | 0.0935 | 0.6 | 0.0935 | 1.73 | 0.5 | 0.5 | 0 | 0.3 | 0.25 | 0.91 | 0 | 0.45 | 0.75 | 0.2 | 0 | 1.65 | 0.6 | 0.25 | 1.0266
|  | Total | 2.23 | 0.645 | 1 | 0.15 | 2.4 | 0.187 | 0.6 | 0.187 | 3.46 | 2.4996 | 1 | 2.8032 | 1.74 | 2.2557 | 1.838 | 3.5011 | 1.05 | 1.6498 | 2.78 | 7.6781 | 3.1393 | 0.6 | 0.5 | 1.0266 | 21.7373 | 23.1831 | 21.7373 | 23.1831
|  | In FASTTRACK Proposal | 2.23 | #REF! | 1 | #REF! | 2.4 | #REF! | 0.6 | #REF! | 3.46 | #REF! | 1 | #REF! | 1.74 | #REF! | 1.838 | #REF! | 1.05 | #REF! | 2.78 | #REF! | 3.1393 | #REF! | 0.5 | #REF!
|  | Material Grand-Total | 5.63 | [5 empty] | 4.06 |  |  |  | 2.74 |  |  |  | 5.668 | [5 empty] | 3.6393
|  | Personnel Grand-Total | 0.982 | [5 empty] | 2.6866 |  |  |  | 5.0589 |  |  |  | 12.829 | [5 empty] | 1.6266
|  | Personnel Grand-Total in FASTTRACK | #REF! | [5 empty] | #REF! |  |  |  | #REF! |  |  |  | #REF! | [5 empty] | #REF!

## TecProfiles
MA | Simulation studies
MB | Studies of Thermodynamics & Heat Transfer
MC | Materials Science & Engineering
MD | Manufacturing & Production
ME | Design & Drafting
MF | Control Systems & Mechatronics
MG | Control Systems & Mechatronics
EA | Analog electronics design (frontends, RF, advanced PCB’s)
EB | Digital electronics design (DAQ)
EC | Analog IC design
ED | Digital IC design
EE | Technical support (cables/mechatronics/integration etc)
CA | Software engineering for embedded or data acquisition
CB | Software engineering for control systems (SCADA)
CC | Software engineering for analysis frameworks /simulations
CD | System administration and network administration support