## NetFelix
Optional
Description of Activity | Nikhef Project | Deliverable Type | FASTTRACK WP | Cost (MEUR) | Q2/2026-Q1/2027 | Q2/2027-Q1/2028 | Q2/2028-Q1/2029 | Q2/2029-Q1/2030 | Q2/2030-Q1/2031 | Q2/2031-Q1/2032 | Q2/2032-Q1/2033 | Q2/2033-Q1/2034 | Q2/2034-Q1/2035 | Q2/2035-Q1/2036
NetFelix | Common DAQ Project | MoU | WP3.2 DAQ |  | 0.2EB¦0.1CA | 0.4EB¦0.2CA | 0.6EB¦0.3CA | 2.7EB¦0.9CA | 2.7EB¦0.9CA | 2.7EB¦0.9CA | 2.7EB¦0.9CA | 1.8EB¦0.9CA | 0.6EB¦0.6CA | 0.2EB¦0.6CA
NetFelix manpower is estimated modulating over time three people with an EB profile and one with a CA profile, with the following specializations:
EB 1) General design and firmware coordination
EB 2) Timing distribution with the high precision required by FASTTRACK detectors
EB 2) Data-transmission protocols, Forward Error Corrections etc.
CA 1) Support to hardware/firmware development, low-level NetFelix tools
This total manpower is then divided over ATLAS/ALICE/LHCb/R&D with the fractions 0.1/0.35/0.35/0.2, respectively
Time modulation ensures a smooth transition of the personpower from ATLAS Phase 2 (Felix) to NetFelix

## ALICE
Optional
Description of Activity | Nikhef Project | Deliverable Type | FASTTRACK WP | Cost (MEUR) |  | Q2/2026-Q1/2027 | Q2/2027-Q1/2028 | Q2/2028-Q1/2029 | Q2/2029-Q1/2030 | Q2/2030-Q1/2031 | Q2/2031-Q1/2032 | Q2/2032-Q1/2033 | Q2/2033-Q1/2034 | Q2/2034-Q1/2035 | Q2/2035-Q1/2036
Sensors | ALICE Project 1 | MoU | WP1.2 Monolithic | 0.3 | 5.3
DAQ | ALICE Project 1 | MoU | WP3.1 High-Speed Transmission | 0.2
Module Design | ALICE Project 1 | MoU | WP4.1 Module Construction | 0.3
Module Cooling | ALICE Project 2 | MoU | WP4.2 Cooling | 0.3
Layout & Construction | ALICE Project 2 | MoU | WP4.3 Mechanics & Infrastructure | 1.2 |  |  |  |  | 0.5ME¦2MD | 0.3ME¦2MD¦0.3MF | 0.2ME¦2MD¦0.5MF | 2MD¦0.2ME¦1MF | 1.5MD¦1MF | 1MD¦0.5MF | 1MD
Module Assembly | ALICE Project 1 | MoU | WP4.1 Module Construction | 0.2
Cooling | ALICE Project 2 | MoU | WP4.2 Cooling | 0.3
ASIC Design | Alice Project 3 | MoU | WP2.2 Monolithic | 0
High Speed links | Alice Project 3 | MoU | WP3.1 High-Speed Transmission | 0.3
NetFelix | Common DAQ Project | MoU | WP3.2 Data Acquisition | 0.7 |  | 0.07EB¦0.035CA | 0.14EB¦0.07CA | 0.21EB¦0.105CA | 0.945EB¦0.315CA | 0.945EB¦0.315CA | 0.945EB¦0.315CA | 0.945EB¦0.315CA | 0.63EB¦0.315CA | 0.21EB¦0.21CA | 0.07EB¦0.21CA
Common Funds (Sensors) |  | MoU-CF | WP1.2 Monolithic | 0.5 |  |  |  |  | 1EE | 1EE¦0.5EA | 1EE¦0.5EA | 1EE | 1EE | 1EE | 1EE
Common Funds (DAQ) |  | MoU-CF | WP3.2 Data Acquisition | 0.5
Common Funds (Infrastructure) |  | MoU-CF | WP4.3 Mechanics & Infrastructure | 0.25
Common Funds (Computing) |  | MoU-CF | WP5.2 Algorithms | 0.25
Sensor Submission | ALICE Project 1 | R&D | WP1.2 Monolithic | 1 |  | 0.5EE¦0.5EA | 0.5EA¦0.7EE | 0.5EA¦1EE¦0.2EB
Sensor Characterization | ALICE Project 1 | R&D | WP1.2 Monolithic | 0.4 |  | 0.1MG | 0.2MG | 0.3MG | 0.2MG | 0.3MG | 0.3MG | 0.3MG | 0.1MG | 0.1MG | 0.1MG
Digital Characterization | Alice Project 3 | R&D | WP2.2 Monolithic | 0.4
Sensor R&D | Alice Project 1 | R&D | WP1.2 Monolithic,WP2.2 Monolithic | 0 | 2.8 | 0.7EC ¦ 0.3ED | 1EC¦0.5ED | 0.5EC¦0.5ED | 0.3EC¦0.4ED
DAQ R&D | Alice Project 3 | R&D | WP3.2 Data Acquisition | 0.1
Module R&D | ALICE Project 1 | R&D | WP4.1 Module Construction | 0.2
Mechanics R&D | ALICE Project 2 | R&D | WP4.3 Mechanics & Infrastructure | 0.2 |  | 1ME¦0.25MA¦0.25MB¦1MD | 1ME¦0.5MA¦0.5MB¦1MD | 1ME¦0.5MA¦0.5MB¦1.5MD
Computing R&D | Alice Project 1 | R&D | WP5.1 Accelerators ,WP5.2 Algorithms | 0.5 |  |  |  | 0.5CC | 0.5CC | 0.5CC | 0.5CC | 0.5CC | 0.5CC
Unforseen material (10% of MoU) |  | Contingency | All WP's | 0.53 | 1.06
Unforseen T.P. (10% of MoU) |  | Contingency | All WP's | 0.53
8.1

## ATLAS
[9 empty] | Sensor final | Sensor production | Wafer production, die, etc.
[6 empty] | Prepare Infrastructure | Sensor R&D | Sensor R&D | prepare module | Module R&D | Module final, QA R&D | Full-scale demonstrator | Production QA | Integration surface | Installation,commissioning
Description of Activity | Nikhef Project | Deliverable Type | FASTTRACK WP | Cost (MEUR) |  | Q2/2026-Q1/2027 | Q2/2027-Q1/2028 | Q2/2028-Q1/2029 | Q2/2029-Q1/2030 | Q2/2030-Q1/2031 | Q2/2031-Q1/2032 | Q2/2032-Q1/2033 | Q2/2033-Q1/2034 | Q2/2034-Q1/2035 | Q2/2035-Q1/2036
Sensors | ATLAS upgrade | MoU | WP1.3 LGAD Hybrids | 0.4 | 1.24 |  |  |  |  | 0.1ME¦0.1EA | 0.05ME¦0.05EA |  |  |  |  | NB: production level work (wafer probe etc)
ASICs | ATLAS upgrade | MoU | WP2.1 Hybrid ASICs | 0.15 | [6 empty] | 0.1EA | 0.1EA | 0.1EA |  |  | NB: Local solution to connect DAQ with ASIC or module characterisation (ASIC part here)
High Speed Link | Common LHC DAQ NetFELIX | MoU | WP3.1 High-Speed Transmission | 0.05 | [10 empty] | 0.2CA
NetFelix | Common LHC DAQ |  | WP3.2 DAQ |  |  | 0.02EB¦0.01CA | 0.04EB¦0.02CA | 0.06EB¦0.03CA | 0.27EB¦0.09CA | 0.27EB¦0.09CA | 0.27EB¦0.09CA | 0.27EB¦0.09CA | 0.18EB¦0.09CA | 0.06EB¦0.06CA | 0.02EB¦0.06CA
DAQ (hw, fw, sw) | Common LHC DAQ NetFELIX | MoU | WP3.2 DAQ | 0.15 |  | 0.1EB¦0.1CA | 0.05EA¦0.05CA | 0.1EA¦0.1CA | 0.05EA¦0.1EB¦0.05CA | 0.05EA¦0.1EB¦0.1CA | 0.05EA¦0.1CA | 0.05CA |  | 0.05EB | 0.05EB¦0.1CA | NB: carrier board etc, modify fw accordingly, readout sw (low-level communication)
Electronics, Cable and Power Supply | ATLAS upgrade | MoU | WP4.3 Mechanics & Infrastructure | 0.08 | [6 empty] | 0.4EE | 0.4EE |  |  | 0.1EE
Module Production | ATLAS upgrade | MoU | WP4.1 Module Construction | 0.25 | [6 empty] | 0.8MF¦0.2MD | 0.4MF¦0.2MD | 0.1MF¦0.1MD
Integration & Commissioning | ATLAS upgrade | MoU | WP4.3 Mechanics & Infrastructure | 0.08 |  | 0.25MD | 0.25MD | [5 empty] | 0.5EE | 0.6EE | 0.8EE | [TBC] to verify if MT needed or not? If so, what category (I assume some level but we can also rely on sending EE people to CERN and use cern mechanics resource)
Computing (a) | AI tracking | MoU | WP5.1 Accelerators, WP5.2 Algorithms | 0.08 |  |  | 0.05CC | 0.1CC | 0.2CC | 0.4CC | 0.2CC | 0.2CC | 0.1CC |  |  | [TBC] Which category under CT? higher FTE needed? If so, when? Any common strategy with AI & PDP?
Sensor Submission | ATLAS upgrade | R&D | WP1.3 LGAD Hybrids | 0.15 | 1.06 | [10 empty] | NB: material only, no engineer needed
Sensor R&D (lab, testbeam) | ATLAS upgrade | R&D | WP1.3 LGAD Hybrids | 0.18 |  |  | 0.1ME¦0.1EA | 0.4ME¦0.6EA | 0.1ME¦0.7EA | 0.1EA | 0.1EA |  |  |  |  | NB: incl. carrier board, ASIC hybridisation for R&D
Radiation (b) | ATLAS upgrade | R&D | WP1.3 LGAD Hybrids | 0.05 |  | 0.3ME¦0.2EA | 0.1ME¦0.1EA | [8 empty] | NB: radiation infrastructure from scratch
Module, QA R&D | ATLAS upgrade | R&D | WP4.1 Module Construction | 0.4 |  |  |  |  | 0.6ME¦0.4EE | 0.8ME¦0.2EE | [5 empty] | [TBC] we need system engineer, which one is it in MT?
Serializer & Data Aggregation (c) | Common LHC DAQ NetFELIX | R&D | WP3.1 High-Speed Transmission | 0.06 |  |  | 0.025EA | 0.025EA¦0.025ED | 0.025EA¦0.025ED | 0.1EA¦0.05ED | 0.1EA | 0.1EA | 0.1EA |  |  | [Q] EA does also packaging and interface?
Optical Power R&D (d) | ATLAS upgrade | R&D | WP4.3 Mechanics & Infrastructure | 0.06 |  | 0.05EA | 0.05EA | 0.05EA | 0.05EA | 0.05EA | 0.05EA | 0.05EA | 0.05EA | 0.05EA | 0.05EA | NB: R&D efforts, without further 4D detector or cross experiments application
Trigger with timing | ATLAS upgrade, AI tracking | R&D | WP5.1 Accelerators, WP5.2 Algorithms | 0.08 |  | 0.05CA | 0.05CA | 0.05CA | 0.05CA | 0.05CA | 0.05CA | 0.05CA | 0.2CA | 0.2CA | 0.2CA
Unforseen R&D Infrastructure | ATLAS upgrade | R&D | WP1.3 LGAD Hybrids, WP2.1 Hybrid ASICs, WP 4.3 Mechanics & Infrastructure | 0.08 |  | 0.025ME¦0.025EA¦0.01CA | 0.025ME¦0.025EA¦0.01CA | 0.05ME¦0.05EA¦0.01ED¦0.01CA | 0.1ME¦0.1EA¦0.01ED¦0.01CA | 0.1ME¦0.025EA¦0.01ED¦0.01CA | 0.025EA¦0.01CA | 0.025EA¦0.01CA
Unforseen material (10% of MoU) |  | Contingency | All WP's | 0.124 | 0.248
Unforseen T.P. (10% of MoU) |  | Contingency | All WP's | 0.124
2.3
Legend | (a) Computing: data processing & trigger (may incl. ML, AI), object reconstruction incl. tracking and forward objects reco in 4D
(b) Radition: cold probe station, cold box at laser setup, cold box at test beam, stoarge and handling of post-radiated sensor/modules
(c) Serializer & Data Aggregation: work following our DRD7 committement from FE (Integrated photonics) to BE (ethernet, server) - both Nikhef & Nijmegen
(d) Optical Power R&D: work following our DRD7 committement on WADAPT (Wu)
Note: | 1) electronics modification relies on international collaborators
2) mechanics/vessel relies on international collaborators
3) AI tracking and Common LHC DAQ NetFELIX are placeholders for the potential Nikhef global projects

## LHCb
Optional
Description of Activity | Nikhef Project | Deliverable Type | FASTTRACK WP | Cost (MEUR) |  | Q2/2026-Q1/2027 | Q2/2027-Q1/2028 | Q2/2028-Q1/2029 | Q2/2029-Q1/2030 | Q2/2030-Q1/2031 | Q2/2031-Q1/2032 | Q2/2032-Q1/2033 | Q2/2033-Q1/2034 | Q2/2034-Q1/2035 | Q2/2035-Q1/2036
Sensors+ASICs | VELO Sensors & ASICs | R&D | WP1.1 3D Hybrids | 4.79 | 4.79 | 0.1MD¦0.1ME¦0.1MG¦0.2EA¦1EC¦1ED¦0.3EE | 0.1MD¦0.1ME¦0.1MG¦0.2EA¦1EC¦1ED¦0.3EE¦0.3CB¦0.3CD | 0.1MD¦0.1ME¦0.1MG¦0.2EA¦1EC¦1ED¦0.3EE¦0.3CB¦0.3CD | 0.1MD¦0.1ME¦0.1MG¦0.9EA¦0.7EB¦1.3EE¦0.3CB¦0.3CD | 0.1MG¦1EA¦0.7EB¦1.3EE¦0.5CB¦0.5CD | 0.1MG¦0.6EA¦0.6EE¦0.5CB¦0.5CD | 0.3EA¦0.3EE¦0.3CB¦0.3CD | 0.3CB¦0.3CD
Controls and DAQ | VELO DAQ & Controls | MoU | WP3.1 High-Speed Transmission +WP3.2 DAQ | 0.24 | 4.1473 | 0.3EA¦0.7EB¦0.3EE¦0.4CA¦0.3CB | 0.3EA¦0.7EB¦0.3EE¦0.4CA¦0.3CB | 0.3EA¦0.7EB¦0.3EE¦0.4CA¦0.3CB | 0.3EA¦0.7EB¦0.3EE¦0.4CA¦0.3CB | 0.3EA¦0.7EB¦0.3EE¦0.4CA¦0.3CB | 0.3EA¦0.7EB¦0.3EE¦0.4CA¦0.3CB | 1EB¦0.7EE¦0.4CA¦0.3CB | 1EB¦0.7EE¦0.5CA¦0.5CB | 1EB¦0.7EE¦0.5CA¦0.5CB | 1EB¦0.7EE¦0.2CA¦0.5CB
NetFelix | Common DAQ Project | MoU | WP3.2 DAQ |  |  | 0.07EB¦0.035CA | 0.14EB¦0.07CA | 0.21EB¦0.105CA | 0.945EB¦0.315CA | 0.945EB¦0.315CA | 0.945EB¦0.315CA | 0.945EB¦0.315CA | 0.63EB¦0.315CA | 0.21EB¦0.21CA | 0.07EB¦0.21CA
RF Shield | VELO RF Shield | MoU | WP4.3 Mechanics & Infrastructure | 0.13 |  | 0.2MA¦0.2MB¦0.4MC¦1MD¦0.2ME | 0.2MA¦0.2MB¦0.4MC¦1MD¦0.2ME¦0.5MF | 1MD¦0.1ME | 1MD¦0.1ME | 1MD¦0.1ME¦0.2MF | 1MD¦0.1ME¦0.2MF | 1MD¦0.1ME¦0.2MF | 1MD¦0.1ME¦0.4MF
Module Production and Cooling | VELO Module Development | MoU | WP4.1 Module Construction | 1.488 |  | 0.2MA¦0.7MB¦0.4MC¦0.4MD¦0.8ME¦0.3MF¦0.1MG¦0.4EA¦0.2EB¦0.2EE¦0.3CA¦0.3CB¦0.1CD | 0.5MB¦0.2MC¦1.2MD¦1.2ME¦0.2MF¦0.1MG¦0.6EA¦0.2EB¦0.2EE¦0.6CA¦0.6CB¦0.1CD | 0.2MB¦0.2MC¦1.2MD¦1.2ME¦0.4MF¦0.2MG¦0.4EA¦0.4EB¦0.8EE¦0.3CA¦0.3CB¦0.1CD | 0.2MB¦0.2MC¦1.2MD¦0.2ME¦0.4MF¦0.2MG¦0.4EA¦0.4EB¦0.8EE¦0.3CA¦0.3CB¦0.1CD | 0.1MB¦1.1MD¦0.5MG¦0.2EA¦0.4EB¦0.8EE¦0.2CA¦0.2CB¦0.1CD | 0.1MB¦1.1MD¦0.5MG¦0.2EA¦0.4EB¦0.8EE¦0.2CA¦0.2CB¦0.1CD | 0.1MB¦1.1MD¦0.5MG¦0.2EA¦0.2EB¦0.8EE¦0.2CA¦0.2CB¦0.1CD | 0.1MB¦0.1MD¦0.1CA¦0.1CD | 0.1MB¦0.1MD¦0.1CA¦0.1CD | 0.1MB¦0.1MD¦0.1CA¦0.1CD
Detector Mechanics | VELO Detector Mechanics | MoU | WP4.3 Mechanics & Infrastructure | 0.8 |  | 0.2MA¦0.2MC¦0.2MD¦0.6ME¦0.2MF¦0.2EE¦0.2CB | 0.4MA¦0.4MC¦0.4MD¦1.2ME¦0.4MF¦0.2EE¦0.4CB | 0.4MA¦0.4MC¦1MD¦1.2ME¦0.4MF¦0.8EE¦0.8CB | 0.2MA¦0.2MC¦1MD¦2ME¦0.4MF¦0.1EE¦0.8CB | 0.2MA¦0.2MC¦1.5MD¦1ME¦0.4MF¦0.1EE¦0.4CB | 0.2MA¦0.2MC¦1.5MD¦2ME¦0.4MF¦0.1EE¦0.2CB | 0.2MA¦0.2MC¦1.5MD¦3ME¦0.4MF¦0.1EE¦0.2CB¦0.2CD | 0.2MA¦0.2MC¦1.5MD¦1ME¦0.4MF¦0.1EE¦0.2CB¦0.2CD | 0.1EE¦0.4CB¦0.2CD | 0.4CB¦0.2CD
Common Funds |  | MoU-CF | WP5.1 Accelerators | 1.4893
Unforseen material (10% of MoU) |  | Contingency | All WP's | 0.41473 | 0.82947
Unforseen T.P. (10% of MoU) |  | Contingency | All WP's | 0.41473
8.9373

## PDP
Optional
Description of Activity | Nikhef Project | Deliverable Type | FASTTRACK WP | Cost (MEUR) |  | Q2/2026-Q1/2027 | Q2/2027-Q1/2028 | Q2/2028-Q1/2029 | Q2/2029-Q1/2030 | Q2/2030-Q1/2031 | Q2/2031-Q1/2032 | Q2/2032-Q1/2033 | Q2/2033-Q1/2034 | Q2/2034-Q1/2035 | Q2/2035-Q1/2036
Accelerators | PDP |  | WP5.1 Accelerators | 1.4 | 1.4 | 0.75CC | 0.75CC¦0.2CD | 0.75CC | 0.75CC | 0.75CC¦0.2CD | 0.75CC | 0.75CC | 0.75CC | 0.75CC | 0.75CC
4D tracking algorithms |  |  | WP5.2 Algorithms

## R&D
Optional
Description of Activity | Nikhef Project | Deliverable Type | FASTTRACK WP | Cost (MEUR) |  | Q2/2026-Q1/2027 | Q2/2027-Q1/2028 | Q2/2028-Q1/2029 | Q2/2029-Q1/2030 | Q2/2030-Q1/2031 | Q2/2031-Q1/2032 | Q2/2032-Q1/2033 | Q2/2033-Q1/2034 | Q2/2034-Q1/2035 | Q2/2035-Q1/2036
Sensors | DR&D |  | WP1.1/WP1.2/WP1.3 | 0.3 | 0.5 | 0.1EA¦0.1MD | 0.1EA¦0.1MD | 0.1EA¦0.1MD | 0.1EA¦0.1MD | 0.1EA¦0.1MD | 0.1EA¦0.1MD | 0.1EA¦0.1MD | 0.1EA¦0.1MD | 0.1EA¦0.1MD | 0.1EA¦0.1MD
NetFelix | Common DAQ |  | WP3.2 |  |  | 0.04EB¦0.02CA | 0.08EB¦0.04CA | 0.12EB¦0.06CA | 0.54EB¦0.18CA | 0.54EB¦0.18CA | 0.54EB¦0.18CA | 0.54EB¦0.18CA | 0.36EB¦0.18CA | 0.12EB¦0.12CA | 0.04EB¦0.12CA
ASIC | DR&D |  | WP2.1/WP2.2 | 0.2 |  |  |  | 1EC¦1ED | 1EC¦1ED | 1EC¦1ED | 1EC¦1ED | 1EC¦1ED | 1EC¦1ED | 1EC¦1ED | 1EC¦1ED

## TecProfiles
MA | Simulation studies
MB | Studies of Thermodynamics & Heat Transfer
MC | Materials Science & Engineering
MD | Manufacturing & Production
ME | Design & Drafting
MF | Control Systems & Mechatronics
MG | Wire Bonding
EA | Analog electronics design (frontends, RF, advanced PCB’s)
EB | Digital electronics design (DAQ)
EC | Analog IC design
ED | Digital IC design
EE | Technical support (cables/mechatronics/integration etc)
CA | Software engineering for embedded or data acquisition
CB | Software engineering for control systems (SCADA)
CC | Software engineering for analysis frameworks /simulations
CD | System administration and network administration support

## SummaryTables
Id | Description | Year | ALICE | ATLAS | LHCb | PDP | R&D
MA | Simulation studies | 1 | 0.25 | 0 | 0.6 | 0 | 0
MA | Simulation studies | 2 | 0.5 | 0 | 0.6 | 0 | 0
MA | Simulation studies | 3 | 0.5 | 0 | 0.4 | 0 | 0
MA | Simulation studies | 4 | 0 | 0 | 0.2 | 0 | 0
MA | Simulation studies | 5 | 0 | 0 | 0.2 | 0 | 0
MA | Simulation studies | 6 | 0 | 0 | 0.2 | 0 | 0
MA | Simulation studies | 7 | 0 | 0 | 0.2 | 0 | 0
MA | Simulation studies | 8 | 0 | 0 | 0.2 | 0 | 0
MA | Simulation studies | 9 | 0 | 0 | 0 | 0 | 0
MA | Simulation studies | 10 | 0 | 0 | 0 | 0 | 0
MA | Simulation studies | Total | 1.25 | 0 | 2.6 | 0 | 0
MB | Studies of Thermodynamics & Heat Transfer | 1 | 0.25 | 0 | 0.9 | 0 | 0
MB | Studies of Thermodynamics & Heat Transfer | 2 | 0.5 | 0 | 0.7 | 0 | 0
MB | Studies of Thermodynamics & Heat Transfer | 3 | 0.5 | 0 | 0.2 | 0 | 0
MB | Studies of Thermodynamics & Heat Transfer | 4 | 0 | 0 | 0.2 | 0 | 0
MB | Studies of Thermodynamics & Heat Transfer | 5 | 0 | 0 | 0.1 | 0 | 0
MB | Studies of Thermodynamics & Heat Transfer | 6 | 0 | 0 | 0.1 | 0 | 0
MB | Studies of Thermodynamics & Heat Transfer | 7 | 0 | 0 | 0.1 | 0 | 0
MB | Studies of Thermodynamics & Heat Transfer | 8 | 0 | 0 | 0.1 | 0 | 0
MB | Studies of Thermodynamics & Heat Transfer | 9 | 0 | 0 | 0.1 | 0 | 0
MB | Studies of Thermodynamics & Heat Transfer | 10 | 0 | 0 | 0.1 | 0 | 0
MB | Studies of Thermodynamics & Heat Transfer | Total | 1.25 | 0 | 2.6 | 0 | 0
MC | Materials Science & Engineering | 1 | 0 | 0 | 1 | 0 | 0
MC | Materials Science & Engineering | 2 | 0 | 0 | 1 | 0 | 0
MC | Materials Science & Engineering | 3 | 0 | 0 | 0.6 | 0 | 0
MC | Materials Science & Engineering | 4 | 0 | 0 | 0.4 | 0 | 0
MC | Materials Science & Engineering | 5 | 0 | 0 | 0.2 | 0 | 0
MC | Materials Science & Engineering | 6 | 0 | 0 | 0.2 | 0 | 0
MC | Materials Science & Engineering | 7 | 0 | 0 | 0.2 | 0 | 0
MC | Materials Science & Engineering | 8 | 0 | 0 | 0.2 | 0 | 0
MC | Materials Science & Engineering | 9 | 0 | 0 | 0 | 0 | 0
MC | Materials Science & Engineering | 10 | 0 | 0 | 0 | 0 | 0
MC | Materials Science & Engineering | Total | 0 | 0 | 3.8 | 0 | 0
MD | Manufacturing & Production | 1 | 1 | 0.25 | 1.7 | 0 | 0.1
MD | Manufacturing & Production | 2 | 1 | 0.25 | 2.7 | 0 | 0.1
MD | Manufacturing & Production | 3 | 1.5 | 0 | 3.3 | 0 | 0.1
MD | Manufacturing & Production | 4 | 2 | 0 | 3.3 | 0 | 0.1
MD | Manufacturing & Production | 5 | 2 | 0 | 3.6 | 0 | 0.1
MD | Manufacturing & Production | 6 | 2 | 0.2 | 3.6 | 0 | 0.1
MD | Manufacturing & Production | 7 | 2 | 0.2 | 3.6 | 0 | 0.1
MD | Manufacturing & Production | 8 | 1.5 | 0.1 | 2.6 | 0 | 0.1
MD | Manufacturing & Production | 9 | 1 | 0 | 0.1 | 0 | 0.1
MD | Manufacturing & Production | 10 | 1 | 0 | 0.1 | 0 | 0.1
MD | Manufacturing & Production | Total | 15 | 1 | 24.6 | 0 | 1
ME | Design & Drafting | 1 | 1 | 0.325 | 1.7 | 0 | 0
ME | Design & Drafting | 2 | 1 | 0.225 | 2.7 | 0 | 0
ME | Design & Drafting | 3 | 1 | 0.45 | 2.6 | 0 | 0
ME | Design & Drafting | 4 | 0.5 | 0.8 | 2.4 | 0 | 0
ME | Design & Drafting | 5 | 0.3 | 1 | 1.1 | 0 | 0
ME | Design & Drafting | 6 | 0.2 | 0.05 | 2.1 | 0 | 0
ME | Design & Drafting | 7 | 0.2 | 0 | 3.1 | 0 | 0
ME | Design & Drafting | 8 | 0 | 0 | 1.1 | 0 | 0
ME | Design & Drafting | 9 | 0 | 0 | 0 | 0 | 0
ME | Design & Drafting | 10 | 0 | 0 | 0 | 0 | 0
ME | Design & Drafting | Total | 4.2 | 2.85 | 16.8 | 0 | 0
MF | Control Systems & Mechatronics | 1 | 0 | 0 | 0.5 | 0 | 0
MF | Control Systems & Mechatronics | 2 | 0 | 0 | 1.1 | 0 | 0
MF | Control Systems & Mechatronics | 3 | 0 | 0 | 0.8 | 0 | 0
MF | Control Systems & Mechatronics | 4 | 0 | 0 | 0.8 | 0 | 0
MF | Control Systems & Mechatronics | 5 | 0.3 | 0 | 0.6 | 0 | 0
MF | Control Systems & Mechatronics | 6 | 0.5 | 0.8 | 0.6 | 0 | 0
MF | Control Systems & Mechatronics | 7 | 1 | 0.4 | 0.6 | 0 | 0
MF | Control Systems & Mechatronics | 8 | 1 | 0.1 | 0.8 | 0 | 0
MF | Control Systems & Mechatronics | 9 | 0.5 | 0 | 0 | 0 | 0
MF | Control Systems & Mechatronics | 10 | 0 | 0 | 0 | 0 | 0
MF | Control Systems & Mechatronics | Total | 3.3 | 1.3 | 5.8 | 0 | 0
MG | Wire Bonding | 1 | 0.1 | 0 | 0.2 | 0 | 0
MG | Wire Bonding | 2 | 0.2 | 0 | 0.2 | 0 | 0
MG | Wire Bonding | 3 | 0.3 | 0 | 0.3 | 0 | 0
MG | Wire Bonding | 4 | 0.2 | 0 | 0.3 | 0 | 0
MG | Wire Bonding | 5 | 0.3 | 0 | 0.6 | 0 | 0
MG | Wire Bonding | 6 | 0.3 | 0 | 0.6 | 0 | 0
MG | Wire Bonding | 7 | 0.3 | 0 | 0.5 | 0 | 0
MG | Wire Bonding | 8 | 0.1 | 0 | 0 | 0 | 0
MG | Wire Bonding | 9 | 0.1 | 0 | 0 | 0 | 0
MG | Wire Bonding | 10 | 0.1 | 0 | 0 | 0 | 0
MG | Wire Bonding | Total | 2 | 0 | 2.7 | 0 | 0
EA | Analog electronics design (frontends, RF, advanced PCB’s) | 1 | 0.5 | 0.275 | 0.9 | 0 | 0.1
EA | Analog electronics design (frontends, RF, advanced PCB’s) | 2 | 0.5 | 0.35 | 1.1 | 0 | 0.1
EA | Analog electronics design (frontends, RF, advanced PCB’s) | 3 | 0.5 | 0.825 | 0.9 | 0 | 0.1
EA | Analog electronics design (frontends, RF, advanced PCB’s) | 4 | 0 | 0.925 | 1.6 | 0 | 0.1
EA | Analog electronics design (frontends, RF, advanced PCB’s) | 5 | 0.5 | 0.425 | 1.5 | 0 | 0.1
EA | Analog electronics design (frontends, RF, advanced PCB’s) | 6 | 0.5 | 0.475 | 1.1 | 0 | 0.1
EA | Analog electronics design (frontends, RF, advanced PCB’s) | 7 | 0 | 0.275 | 0.5 | 0 | 0.1
EA | Analog electronics design (frontends, RF, advanced PCB’s) | 8 | 0 | 0.25 | 0 | 0 | 0.1
EA | Analog electronics design (frontends, RF, advanced PCB’s) | 9 | 0 | 0.05 | 0 | 0 | 0.1
EA | Analog electronics design (frontends, RF, advanced PCB’s) | 10 | 0 | 0.05 | 0 | 0 | 0.1
EA | Analog electronics design (frontends, RF, advanced PCB’s) | Total | 2.5 | 3.9 | 7.6 | 0 | 1
EB | Digital electronics design (DAQ) | 1 | 0.07 | 0.12 | 0.97 | 0 | 0.04
EB | Digital electronics design (DAQ) | 2 | 0.14 | 0.04 | 1.04 | 0 | 0.08
EB | Digital electronics design (DAQ) | 3 | 0.41 | 0.06 | 1.31 | 0 | 0.12
EB | Digital electronics design (DAQ) | 4 | 0.945 | 0.37 | 2.745 | 0 | 0.54
EB | Digital electronics design (DAQ) | 5 | 0.945 | 0.37 | 2.745 | 0 | 0.54
EB | Digital electronics design (DAQ) | 6 | 0.945 | 0.27 | 2.045 | 0 | 0.54
EB | Digital electronics design (DAQ) | 7 | 0.945 | 0.27 | 2.145 | 0 | 0.54
EB | Digital electronics design (DAQ) | 8 | 0.63 | 0.18 | 1.63 | 0 | 0.36
EB | Digital electronics design (DAQ) | 9 | 0.21 | 0.11 | 1.21 | 0 | 0.12
EB | Digital electronics design (DAQ) | 10 | 0.07 | 0.07 | 1.07 | 0 | 0.04
EB | Digital electronics design (DAQ) | Total | 5.31 | 1.86 | 16.91 | 0 | 2.92
EC | Analog IC design | 1 | 0.7 | 0 | 1 | 0 | 0
EC | Analog IC design | 2 | 1 | 0 | 1 | 0 | 0
EC | Analog IC design | 3 | 0.5 | 0 | 1 | 0 | 1
EC | Analog IC design | 4 | 0.3 | 0 | 0 | 0 | 1
EC | Analog IC design | 5 | 0 | 0 | 0 | 0 | 1
EC | Analog IC design | 6 | 0 | 0 | 0 | 0 | 1
EC | Analog IC design | 7 | 0 | 0 | 0 | 0 | 1
EC | Analog IC design | 8 | 0 | 0 | 0 | 0 | 1
EC | Analog IC design | 9 | 0 | 0 | 0 | 0 | 1
EC | Analog IC design | 10 | 0 | 0 | 0 | 0 | 1
EC | Analog IC design | Total | 2.5 | 0 | 3 | 0 | 8
ED | Digital IC design | 1 | 0.3 | 0 | 1 | 0 | 0
ED | Digital IC design | 2 | 0.5 | 0 | 1 | 0 | 0
ED | Digital IC design | 3 | 0.5 | 0.035 | 1 | 0 | 1
ED | Digital IC design | 4 | 0.4 | 0.035 | 0 | 0 | 1
ED | Digital IC design | 5 | 0 | 0.06 | 0 | 0 | 1
ED | Digital IC design | 6 | 0 | 0 | 0 | 0 | 1
ED | Digital IC design | 7 | 0 | 0 | 0 | 0 | 1
ED | Digital IC design | 8 | 0 | 0 | 0 | 0 | 1
ED | Digital IC design | 9 | 0 | 0 | 0 | 0 | 1
ED | Digital IC design | 10 | 0 | 0 | 0 | 0 | 1
ED | Digital IC design | Total | 1.7 | 0.13 | 3 | 0 | 8
EE | Technical support (cables/mechatronics/integration etc) | 1 | 0.5 | 0 | 1 | 0 | 0
EE | Technical support (cables/mechatronics/integration etc) | 2 | 0.7 | 0 | 1 | 0 | 0
EE | Technical support (cables/mechatronics/integration etc) | 3 | 1 | 0 | 2.2 | 0 | 0
EE | Technical support (cables/mechatronics/integration etc) | 4 | 1 | 0.4 | 2.5 | 0 | 0
EE | Technical support (cables/mechatronics/integration etc) | 5 | 1 | 0.2 | 2.5 | 0 | 0
EE | Technical support (cables/mechatronics/integration etc) | 6 | 1 | 0.4 | 1.8 | 0 | 0
EE | Technical support (cables/mechatronics/integration etc) | 7 | 1 | 0.4 | 1.9 | 0 | 0
EE | Technical support (cables/mechatronics/integration etc) | 8 | 1 | 0.5 | 0.8 | 0 | 0
EE | Technical support (cables/mechatronics/integration etc) | 9 | 1 | 0.6 | 0.8 | 0 | 0
EE | Technical support (cables/mechatronics/integration etc) | 10 | 1 | 0.9 | 0.7 | 0 | 0
EE | Technical support (cables/mechatronics/integration etc) | Total | 9.2 | 3.4 | 15.2 | 0 | 0
CA | Software engineering for embedded or data acquisition | 1 | 0.035 | 0.17 | 0.735 | 0 | 0.02
CA | Software engineering for embedded or data acquisition | 2 | 0.07 | 0.13 | 1.07 | 0 | 0.04
CA | Software engineering for embedded or data acquisition | 3 | 0.105 | 0.19 | 0.805 | 0 | 0.06
CA | Software engineering for embedded or data acquisition | 4 | 0.315 | 0.2 | 1.015 | 0 | 0.18
CA | Software engineering for embedded or data acquisition | 5 | 0.315 | 0.25 | 0.915 | 0 | 0.18
CA | Software engineering for embedded or data acquisition | 6 | 0.315 | 0.25 | 0.915 | 0 | 0.18
CA | Software engineering for embedded or data acquisition | 7 | 0.315 | 0.2 | 0.915 | 0 | 0.18
CA | Software engineering for embedded or data acquisition | 8 | 0.315 | 0.29 | 0.915 | 0 | 0.18
CA | Software engineering for embedded or data acquisition | 9 | 0.21 | 0.26 | 0.81 | 0 | 0.12
CA | Software engineering for embedded or data acquisition | 10 | 0.21 | 0.56 | 0.51 | 0 | 0.12
CA | Software engineering for embedded or data acquisition | Total | 2.205 | 2.5 | 8.605 | 0 | 1.26
CB | Software engineering for control systems (SCADA) | 1 | 0 | 0 | 0.8 | 0 | 0
CB | Software engineering for control systems (SCADA) | 2 | 0 | 0 | 1.6 | 0 | 0
CB | Software engineering for control systems (SCADA) | 3 | 0 | 0 | 1.7 | 0 | 0
CB | Software engineering for control systems (SCADA) | 4 | 0 | 0 | 1.7 | 0 | 0
CB | Software engineering for control systems (SCADA) | 5 | 0 | 0 | 1.4 | 0 | 0
CB | Software engineering for control systems (SCADA) | 6 | 0 | 0 | 1.2 | 0 | 0
CB | Software engineering for control systems (SCADA) | 7 | 0 | 0 | 1 | 0 | 0
CB | Software engineering for control systems (SCADA) | 8 | 0 | 0 | 1 | 0 | 0
CB | Software engineering for control systems (SCADA) | 9 | 0 | 0 | 0.9 | 0 | 0
CB | Software engineering for control systems (SCADA) | 10 | 0 | 0 | 0.9 | 0 | 0
CB | Software engineering for control systems (SCADA) | Total | 0 | 0 | 12.2 | 0 | 0
CC | Software engineering for analysis frameworks /simulations | 1 | 0 | 0 | 0 | 0.75 | 0
CC | Software engineering for analysis frameworks /simulations | 2 | 0 | 0.05 | 0 | 0.75 | 0
CC | Software engineering for analysis frameworks /simulations | 3 | 0.5 | 0.1 | 0 | 0.75 | 0
CC | Software engineering for analysis frameworks /simulations | 4 | 0.5 | 0.2 | 0 | 0.75 | 0
CC | Software engineering for analysis frameworks /simulations | 5 | 0.5 | 0.4 | 0 | 0.75 | 0
CC | Software engineering for analysis frameworks /simulations | 6 | 0.5 | 0.2 | 0 | 0.75 | 0
CC | Software engineering for analysis frameworks /simulations | 7 | 0.5 | 0.2 | 0 | 0.75 | 0
CC | Software engineering for analysis frameworks /simulations | 8 | 0.5 | 0.1 | 0 | 0.75 | 0
CC | Software engineering for analysis frameworks /simulations | 9 | 0 | 0 | 0 | 0.75 | 0
CC | Software engineering for analysis frameworks /simulations | 10 | 0 | 0 | 0 | 0.75 | 0
CC | Software engineering for analysis frameworks /simulations | Total | 3 | 1.25 | 0 | 7.5 | 0
CD | System administration and network administration support | 1 | 0 | 0 | 0.1 | 0 | 0
CD | System administration and network administration support | 2 | 0 | 0 | 0.4 | 0.2 | 0
CD | System administration and network administration support | 3 | 0 | 0 | 0.4 | 0 | 0
CD | System administration and network administration support | 4 | 0 | 0 | 0.4 | 0 | 0
CD | System administration and network administration support | 5 | 0 | 0 | 0.6 | 0.2 | 0
CD | System administration and network administration support | 6 | 0 | 0 | 0.6 | 0 | 0
CD | System administration and network administration support | 7 | 0 | 0 | 0.6 | 0 | 0
CD | System administration and network administration support | 8 | 0 | 0 | 0.6 | 0 | 0
CD | System administration and network administration support | 9 | 0 | 0 | 0.3 | 0 | 0
CD | System administration and network administration support | 10 | 0 | 0 | 0.3 | 0 | 0
CD | System administration and network administration support | Total | 0 | 0 | 4.3 | 0.4 | 0
|  |  | 53.415 | 18.19 | 129.715 | 7.9 | 22.18
Group | Description | Year | ALICE | ATLAS | LHCb | PDP | R&D
MT | Mechanical Technology | 1 | 2.6 | 0.575 | 6.6 | 0 | 0.1
MT | Mechanical Technology | 2 | 3.2 | 0.475 | 9 | 0 | 0.1
MT | Mechanical Technology | 3 | 3.8 | 0.45 | 8.2 | 0 | 0.1
MT | Mechanical Technology | 4 | 2.7 | 0.8 | 7.6 | 0 | 0.1
MT | Mechanical Technology | 5 | 2.9 | 1 | 6.4 | 0 | 0.1
MT | Mechanical Technology | 6 | 3 | 1.05 | 7.4 | 0 | 0.1
MT | Mechanical Technology | 7 | 3.5 | 0.6 | 8.3 | 0 | 0.1
MT | Mechanical Technology | 8 | 2.6 | 0.2 | 5 | 0 | 0.1
MT | Mechanical Technology | 9 | 1.6 | 0 | 0.2 | 0 | 0.1
MT | Mechanical Technology | 10 | 1.1 | 0 | 0.2 | 0 | 0.1
ET | Electronic Technlogy | 1 | 2.07 | 0.395 | 4.87 | 0 | 0.14
ET | Electronic Technlogy | 2 | 2.84 | 0.39 | 5.14 | 0 | 0.18
ET | Electronic Technlogy | 3 | 2.91 | 0.92 | 6.41 | 0 | 2.22
ET | Electronic Technlogy | 4 | 2.645 | 1.73 | 6.845 | 0 | 2.64
ET | Electronic Technlogy | 5 | 2.445 | 1.055 | 6.745 | 0 | 2.64
ET | Electronic Technlogy | 6 | 2.445 | 1.145 | 4.945 | 0 | 2.64
ET | Electronic Technlogy | 7 | 1.945 | 0.945 | 4.545 | 0 | 2.64
ET | Electronic Technlogy | 8 | 1.63 | 0.93 | 2.43 | 0 | 2.46
ET | Electronic Technlogy | 9 | 1.21 | 0.76 | 2.01 | 0 | 2.22
ET | Electronic Technlogy | 10 | 1.07 | 1.02 | 1.77 | 0 | 2.14
CT | Computer Technlogy | 1 | 0.035 | 0.17 | 1.635 | 0.75 | 0.02
CT | Computer Technlogy | 2 | 0.07 | 0.18 | 3.07 | 0.95 | 0.04
CT | Computer Technlogy | 3 | 0.605 | 0.29 | 2.905 | 0.75 | 0.06
CT | Computer Technlogy | 4 | 0.815 | 0.4 | 3.115 | 0.75 | 0.18
CT | Computer Technlogy | 5 | 0.815 | 0.65 | 2.915 | 0.95 | 0.18
CT | Computer Technlogy | 6 | 0.815 | 0.45 | 2.715 | 0.75 | 0.18
CT | Computer Technlogy | 7 | 0.815 | 0.4 | 2.515 | 0.75 | 0.18
CT | Computer Technlogy | 8 | 0.815 | 0.39 | 2.515 | 0.75 | 0.18
CT | Computer Technlogy | 9 | 0.21 | 0.26 | 2.01 | 0.75 | 0.12
CT | Computer Technlogy | 10 | 0.21 | 0.56 | 1.71 | 0.75 | 0.12